## Defect Tracker
Sl No | Submitted Date | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status(Opened/Closed) | Remarks
1 | 2025-11-27 | OCR not correctly extracting applicant details from passport image | Sprint 1 | Backend Team | Functional | Improved image preprocessing, added noise removal | 2025-11-28 | closed | OCR accuracy improved, extraction errors reduced
2 | 2025-11-29 | Missing values causing incorrect visa approval prediction | Sprint 2 | Backend Team | Functional | Implemented data validation checks and default handling for missing fields | 2025-11-30 | closed | Prediction accuracy stabilized after fix
3 | 2025-12-06 | Regression model accuracy not matching validation results | Sprint 2 | ML Team | Algorithmic | Re-evaluated feature selection and retrained model with updated dataset | 2025-12-07 | closed | Model performance now consistent with validation results
4 | 2025-12-10 | Processing time estimator showing negative values | Sprint 2 | ML Team | Logic | Corrected calculation logic and added boundary condition check | 2025-12-11 | closed | Negative values eliminated
5 | 2025-12-12 | Visa status result not displayed on UI after prediction | Sprint 3 | Frontend Team | UI/Validation | Fixed API response binding and UI state update logic | 2025-12-13 | closed | Result now displayed correctly on UI
6 | 2025-12-17 | Invalid document upload not handled properly | Sprint 3 | Frontend Team | Error Handling | Added file type, size validation, and proper error messages | 2025-12-18 | closed | Invalid uploads are now blocked with user alerts
7 | 2025-12-26 | API response delay during peak requests | Sprint 3 | Backend Team | Performance | Optimized database queries and enabled caching for frequent requests | 2025-12-27 | closed | Response time improved during high traffic
8 | 2026-01-02 | Dashboard charts not updating after model retraining | Sprint 4 | Frontend Team | Integration | Implemented auto-refresh and backend trigger after retraining | 2026-01-03 | closed | Dashboard reflects latest model results
9 | 2026-01-09 | Incorrect visa rejection reason displayed | Sprint 4 | Backend Team | Functional | Fixed backend mapping logic between prediction output and rejection messages | 2026-01-10 | closed | Correct rejection reason now shown
10 | 2026-01-21 | UI alignment and text formatting issues | Sprint 4 | Frontend Team | UI | Adjusted CSS styles and tested across screen resolutions | 2026-01-22 | closed | UI looks consistent across devices